## Agile Project Plan
CS 5351 Software Engineering (Project) - Group 1 - Optimization of Test Automation
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| To Be Determined | Lee Ho Man | 2020-09-25 | 2020-11-30 |  | 5% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS | Group Member | Role
| Sprint 1 - Determine / Design the basic model of our SE Tools (Test Automation) |  | ALL |  | 2020-10-05 | 2020-10-18 | 13 | Not Started |  | Lee Ho Man (54407825) | Project Manager
| Feature 1 - Work on GUI Capture & Replay Tools |  | Fill your english name here |  | 2020-10-05 | 2020-10-18 | 13 | Not Started |  |  | Software Engineer
| Feature 2 - Work on Selenium IDE |  | Fill your english name here |  | 2020-10-05 | 2020-10-18 | 13 | Not Started |  |  | Software Engineer
| Feature 3 - Research on Paper related to different algorithms of Test Automation |  | Lee Ho Man, Qi Tsanghai |  | 2020-10-05 | 2020-10-18 | 13 | Not Started |  |  | Software Engineer
| Sprint 2 |  | Fill your english name here |  | 2022-09-16 | 2022-09-24 | 8 | In Progress |  |  | Software Engineer
| Feature 4 |  | Fill your english name here |  | 2022-09-16 | 2022-09-17 | 1 | In Progress |  | x
| Feature 5 |  | Fill your english name here |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
| Feature 6 |  | Fill your english name here |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
| Sprint 3 - Finalize the Software Engineering Tools |  | ALL |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 |  | Fill your english name here |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Feature 8 |  | Fill your english name here |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Feature 9 |  | Fill your english name here |  | 2022-10-02 | 2022-10-05 | 3 | Not Started
Milestone 1: Week7 (12-Oct) Workshop. Expect some scenario case studies (my guess)
Milestone 2: I. a 15-mins video II. An Oral Presentation III. A Final report and the Source code --- (All should be done on or before late November)
Template Credit: www.smartsheet.com